## Instructions (hidden)
Instructions
Big picture | A Gap analysis in an implementation project is a highly recommended phase. Its purpose is to present the match of Elico Corp with the Customer's needs and convince him on the feasability of the project. It is also the first phase before the first stage gate that allows the Customer to exit the project with limited investment if the results do not conform to his expectations. Even though it is an optional phase, it will make you save time on the detailed analysis. The goal of a Gap analysis is to determine an estimate of project time and cost at a 70% certainty in a limited time (3 to 15 days).
Steps | 1. The Partner interviews the Customer to list the project requirements and their critical level. They might have to define processes to make sure all requirements are covered. 2. Elico Corp specifies the functional qualification and the development effort estimation, or asks additional details to Partner and Customer. 3. Customer reviews the results and can decide to drop certain requirements that would be too expensive or time consuming.
Reuse | This document is a sample, not a template. You can use it: - to see what the result of a Gap analysis will look like, - to reuse its structure for your project, - to understand the level of detail needed to identify the development effort of a requirement. You should not use the requirements in this document as a starting point to build your own list of requirements because the risk of omitting requirements will increase and their precision related to your project will be altered.
Duration | The time to complete the functional qualification and the development effort estimation is approximately 75 reqs/day once the requirements have a reasonable level of detail. (this sample document presents a reasonable level of detail). In most cases, the party in charge of identifying the implementation effort will need to ask additional questions on certain requirements that are not clear enough or too specific to the project. Therefore, after the first creation of the requirements list, a discussion will take place with the Partner to make sure they are in line on the meaning of the less meaningful requirements.
Skills | The level of knowledge on Elico Corp needed to write the requirements list is small, however it requires to be a business analyst with experience in the field preferably. On the other hand, determining the implementation efforts can only be done by a very exerienced Elico Corp analyst because it implies reusing existing functionalities and hence knowing all certified and major modules thoroughly.
Approach | To create the list of requirements, the Partner should conduct series of interviews with key people in the organization to identify what information they expect the system will provide them. If listing requirements from scratch is too complex, it is encouraged to first define process diagrams (see technical analysis phase of the project) and list requirements based on each step of these processes to make sure you will not omit any. Moreover, it will save time for the detailed analysis phase.
Working with this document | Each spreadsheet, except the "Results" sheet, represents a need category (Eg: invoicing, production planning, products warranty,...). You can organize them the way you see fit according to your project whether it is by department, by business application, or by project phase. In each spreadsheet, you will find: 1. the category name (must be the exact same as the speadsheet name in the tab) 2. the category subtitle: an optional field to add a description to the name. 3. the requirements id: a unique identifier per category. 4. a controller that allows to take or not a requirement into consideration in the results page. 5. the requirements names: a description that all contributors can relate to similarly. 6. the critical level: a score between 1 and 4 that represents the importance of the requirement for the contributors from "nice to have" (1) to "MUST have" (4). The contributors team should agree on the meaning of the scale to avoid subjective scoring. Eg: (4):the company cannot operate without this requirement; (3):a contributor would waste time on manual processing if this requirement wasn't implemented, this requirement was available in the legacy application; (2):the Elico Corp project is intended to bring new features in addition to the legacy system and this requirement is part of the "why" of this project; (1):the long-lasting non-critical dream of a contributor. Moreover, the critical level can be used to determine project phases, starting from the most painful to the least painful for the organization. 7. the system: the name of the application or system that fulfills the requirements at the moment of the analysis. Eg: MS Excel, Quickbooks, Paper. Use "None" if the requirement is not available and will be introduced with Elico Corp. 8. the contributors: the key people in the organization that are impacted by the requirement and have a decision authority on its implementation. 9. the Elico Corp functional qualification: a description of how Elico Corp Inc. recommends to implement the requirement in Elico Corp. 10. the technical qualification elements: an overview of the technical elements to define during the technical analysis. 11. the development effort: a score between 1 and 5 that represents the effort it would take Elico Corp Inc. to implement the requirement. (1):Feature already exists as is in Elico Corp; (2):Feature already exists in Elico Corp and requires configuration (like a rule or a switch), no development involved; (3):Feature doesn't exist in Elico Corp and requires a small (less than 4 hours) custom development (no change in the existing logic); (4):Feature doesn't exist in Elico Corp and either requires a heavy custom development (more than 4 hours) like a new module or a change in the existing logic; (5):Not enough information to identify the necessary development (we need more detail)
Contributors | several people holding key roles in the company will contribute to this document (Eg: head accountant, warehouse manager, VP sales,...). The name and subtitle of each sheet has to be meaningful enough so that if a contributor wants to add a requirements, he will know where to find or add it. When a contributor adds a requirement, he must add his name in the contributor list. When a contributor wants to be part of the discussions related to an existing requirement, he must add his name in the contributor list.
Understanding the results | The Gap Frequency Grid shows the frequency of each "critical level-development effort" combination. This grid is the summary of all categories spreadsheets. A red line will appear next to categories that have a score for the critical level and not for the development effort (or vice versa). This is useful to control data integrity. The development efforts per category is a convenient way of visualizing which categories will require the most effort. The gap chart shows the distribution "critical level-effort". It helps determining the part of the project that will be the most crucial (score 4-4). It also allows to potentially remove from the project scope the requirements with a high effort and a low critical level to decrease the total budget. The total time and cost estimation: takes the Elico Corp qualification into account to determine the time and hence cost necessary for the analysis phase, and takes the development effort into account to determine the time and hence cost necessary for the development phase.
Changelog | v4: Fixed: Drop was not considered for analysis cost calculation (fhe, reported by fpi) Added: calculation of total cost per category and per development effort (fhe) Improved developments effort per category: now on one bar chart and addition of costs as data labels (fhe) Improved headers: readability, frozen panes (fhe, inspired by fpi) Improved control info on Results page (fhe) Improved distinction between Functional and technical Analysis in cost estimation (fhe) v3: Added Control feature (fhe) Fixed Time and cost estimation formulas (fhe) Improved spreadsheet references with INDIRECT for scalability automation (fhe) Improved demo data (fhe) Improved instructions (fhe) Added Deployment and Training/Support/Maintenance in results (fhe) v2: Added Technical qualification elements (fhe) Added analysis time and cost estimation in results (fhe) v1: Initial version (fhe)
Todo | - Costs on Gap Chart - Add project planning proposition - Update instructions for dev 1 = 0.1 day - Detail Deployment - Improve demo data for effort 4 requirements - Add POC concept - Gap Chart for analysis (to be confirmed)

## Sales
Sales | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
[7 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4
dev0204 | Keep | Modify the SO printout in Odoo to group by product item | 1 |  | Eleven | * Add a level of product template with sub-detail per variant in current pdf SO printout | 1 | [12 empty] | 4 | 2
dev0205 | Keep | Make sure the standard EE inter-company connector updates all the supply chain | 1 |  | Eleven | * Standard SO/PO inter-company process * multiple cascade (HHK => SPF => HHF) * Multiple updates |  |  |  | 1 | [9 empty] | 4 | 3
dev0206 | Keep | Report containing SO / linked PO / item/title / qty / Ready date | 2 |  | Eleven | * To be discussed: depends whether the SO and PO are linked as MTO or MTS (cf discussion on strategy for replenishment). * Modify the SO and add the link to the SO lines (about date/PO number) * Create a BI view with relevant information |  |  |  |  | 1 | [8 empty] | 4 | 1
dev0302 | Keep | Create some fields for statistics: Group and Division. Add to main statistics (sales/Purchase/invoices) | 1 |  | Brett | * Create field Group and Division * Add the fields and 'group by' in SO, SI, PO, stock move objects * Add the fields and 'group by' in BI reports | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 4 | 2

## Integration
Integration | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
Integration with Axapta | [6 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | All Kept | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4
dev0201 | Keep | Connector to import Product from Axapta via csv files | 1 | Axapta | GH | * From Axapta to Odoo * Store the Axapta ID of the product * Product name * SKU number * Update the Product when import again * Synchronization log (with status) * Use Odoo connector technology with job queue and retry |  |  |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 4 | 5
dev0202 | Keep | Connector to import BoM from Axapta via csv files | 1 | Axapta | GH | * From Axapta to Odoo * Store the Axapta ID of the BoM * BoM name and Finished Product * BoM structure (including Product ID and UoM * Update the BoM when import again * Synchronization log (with status) * Use Odoo connector technology with job queue and retry |  |  |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 4 | 5
dev0203 | Keep | Connector with Axapta in order to create/update SO in Odoo based on Axapta PO via csv files | 1 | Axapta | Eleven | * From Axapta to Odoo * Store Axapta ID of the PO * Convert the Company of origin into the customer * Create SO and preload information from customer (pricelist, Payment terms etc.) * Synchronize: Currency, Product, Qty, amount * Synchronization log (with status) * Conversion carton => Item based on the BoM * Use Odoo connector technology with job queue and retry |  |  |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 4 | 10

## Products and Materials
Products and Materials | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
[7 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4
dev0101 | Drop | Use website catalog module to publish the barcode information. | 3 | Local system based on Axapta | GH | * install Website and ecommerce without checkout * create a search field in the website * Display the products according to the search content | [5 empty] | 1 | [7 empty] | 4 | 2

## Planning (hidden)
Planning | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
[7 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4

## Manufacturing
Manufacturing | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
[7 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4
dev0301 | Keep | Have a function to calculate finished Product cost based on the components of the BoM | 1 | Axapta | Brett | * Based on the cost of all components and date, the cost of finished product should be calculated based on the BoM and displayed * Possibility to updated the product cost in the product itself |  |  |  |  | 1 | [6 empty] | 1 | 1 | 4 | 3
dev1001 | Drop | Production Date should be triggered/adapted according to component availability. | 3 |  | Cherry | * A wizard in the MO should allow to check the minimum production date based on the Raw Material and PO/WIP * Add link and calculation function to update the availability date at product level |  |  |  |  | 1 | [5 empty] | 1 |  | 1 | 4 | 3

## Warehousing (hidden)
Warehousing | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
[7 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4

## Purchasing
Purchasing | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
[7 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4
dev0402 | Keep | Possibility to have all pending delivery per factory in Excel with information per factory with creation date/expected delivery date/qty/item/leadtime | 1 |  | Anthea | * Modify the Purchase incoming product list menu * Add creation date and supplier |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 4 | 1
dev0407 | Drop | Display the creation date in the pricelist | 3 |  | Anthea | * show the corresponding field in the Pricelist form view and List view * Add the corresponding filter by creation date. |  |  |  |  | 1 | [8 empty] | 2 | 0.25
dev0410 | Keep | Add multiple dates (confirmed/committed/Actual) in the objects and reports as a KPI | 2 |  | Eleven | * Add fields confirmed/committed/Actual * Modify PO and Incoming shipment object * Modify the purchase BI report and Stock BI report |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 4 | 2
dev0401 | Drop | PO version numbers for each SAVE of the PO (similar to current Axapta behavior. | 4 |  | Anthea | * Add a sub-version field * Change the "on save" function * Change the name Display function |  |  | 1 | [10 empty] | 4 | 1
dev0406 | Drop | Add setup and method when the PO is saved to check for special product and change amount based on total PO. | 3 |  | Anthea | * Add set up in the product ("Automatic amount Calculation") * Make sure that when the PO is saved, that if it contains special product the * amount in the product line is recalculated |  |  |  | 1 | [5 empty] | 1 |  |  | 1 | 4 | 5
dev0409 | Keep | Notes in the products/customers/Suppliers to be added to the PO or SO (special attention/remarks) as remarks for QC (with a simple workflow/checkbox "checked" by QC manager). | 2 |  | Anthea / Daisy | * Setup a simple text at product/customer/supplier level * When the product/customer/supplier is added to the PO the remarks are added in the PO * The QC manager can "check" the remark to acknowledge it * For both the SO and PO |  |  | 2 |  | 2 |  |  |  |  | 1 |  |  |  | 4 | 8
dev0901 | Drop | Add a control / mark in PO Line to show that the price is different from original. | 3 |  | Cherry | * add a field and function to store the price history in PO |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 4 | 3

## Shipping
Shipping | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
[7 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4
dev1002 | Drop | Export declaration file (all Chinese) in pdf | 3 |  | Cherry | * 5 pdf reports to be created based on the packing list information and container. | 5 | [8 empty] | 2 |  |  |  | 4 | 15
dev1003 | Keep | Add a control/checkbox to control that the export documents have been printed/approved by the government. | 1 |  | Cherry | * simple checkbox to be added at the DO level. |  |  |  |  | 1 | [8 empty] | 3 | 0.5
dev0408 | Drop | Possibility to manage shipping marks. Multiple choice | 3 |  | Anthea | #. Standard Odoo Attachment (standard in Odoo) #. Notes in the SO/PO (cf dev0409_) #. Create a new model for shipping marks that the user can link to the SO/PO | [13 empty] | 5
dev0403 | Drop | Possibility to group and split PO and SO into multiple containers. | 3 |  | Anthea | * Create an object container with relevant fields about forwarder, PoD, PoA, ETA, ETD (expected/confirmed/actual), etc. * Wizard to assign IS or DO to the container (with location 'transit'). * Possibility to process all SM of the container at once (with states: Draft/Underway/arrived). | [5 empty] | 2 |  |  |  | 2 |  |  | 2 | 4 | 12
dev0404 | Drop | Possibility to create the packing list in the system for multiple PO or SO in one container (linked to dev0403). | 3 |  | Anthea | * detail by PO/Item/title or SO/Item/Title * Same layout as dev0405 |  | 1 | [11 empty] | 4 | 5
dev0405 | Keep | Possibility to create the packing list for customer or supplier delivery in the system. | 1 |  | Anthea, Eleven, Cherry | * First item line then title details * Modify the standard Stock picking report to add the missing fields * GW/NW/CBM (per carton and total) * Some header information based on the container information. |  | 1 | [11 empty] | 4 | 5

## Warranty (hidden)
Warranty | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
[7 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4

## AR-AP
AR-AP | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
[7 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4
dev1101 | Keep | Add a checkbox in Odoo Invoices for fapiao received which would trigger an accounting move from "VAT Fapiao to be received" to "VAT Fapiao received" | 1 |  | Eileen | * when a new fapiao is inserted the VAT should be transferred * if dev1102_ is done, then the accounting entry should be done with the fapiao amount. * if dev1102_ is not done, then acounting entry should be done for the total amount of the commercial invoice. * Set up in the company accounting. |  |  | 1 |  | 1 | [8 empty] | 4 | 3
dev1102 | Drop | Add the list of fapiao received or emitted for a commercial invoice. | 3 |  | Eileen | * Add a list in the commercial invoice and vendor bill * A list to query any fapiao in the system. |  |  |  |  | 2 |  |  |  |  | 1 |  |  |  | 4 | 5
dev1103 | Drop | Develop standard Chinese accounting reports (BS and P&L). | 3 |  | Eileen | * In Excel, follow the standard layout with numbering of the rows. * 2 reports: Balance Sheet and Profit and Loss |  | 2 | [11 empty] | 4 | 8

## Payroll and HR (hidden)
Payroll and HR | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
[7 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4

## Accounts Payable (hidden)
Accounts Payable | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
[7 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4

## Cost Accounting (hidden)
Cost Accounting | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
[7 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4

## GL (hidden)
GL | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
[7 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4

## Security (hidden)
Security | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
[7 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4

## Repricing Service Parts (hidden)
Repricing Service Parts | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
[7 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4

## Quality - In-house
Quality - In-house | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
[7 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4
dev0601 | Keep | Inspection application for QC with date with final inspection date. | 1 |  | Anthea / Daisy | + In Stock Picking header add final inspection date+inspector + Create a calendar view + + Create an automatic mail to inform the user |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 4 | 2
dev0603 | Drop | Have a model for document (from document management system) with versioning. | 3 |  | Daisy | * Use ISO9001 Community Modules * Link the modules to the BoM and MO * If version is provided in SOL, copy to inspection, otherwise take the latest version |  |  | 1 | [6 empty] | 1 |  |  |  | 4 | 3
dev0604 | Keep | In product/supplier, add approved sample checkbox with date for approval | 1 |  | Daisy | * simple field to allow the control of the information in supplierinfo model |  |  |  |  | 1 | [8 empty] | 3 | 0.5
dev0602 | Drop | Create inspection lines in the Stock picking | 2 |  | Daisy | + Multiple fields: Expected date, Confirmed date, Inspection date, Inspector etc. + Workflow management: Pending/Rejected/Passed + Link to Stock Picking model. | [5 empty] | 1 | 1 |  |  | 1 |  |  |  | 4 | 5

## Quality - After Sale (hidden)
Quality - After Sale | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
(related to Warranty) | [6 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4

## Marketing (hidden)
Marketing | [5 empty] | Functional Analysis | [6 empty] | Technical Analysis | [6 empty] | Development
Marketing & customer relationship | [6 empty] | Reports |  | Processes |  | Screens |  | Workflows |  |  |  |  | Wizards
# | Control | Functionality Description | Critical Level | System | Contributors | OpenERP Solution Mapping | Basic Reports | Advanced Reports | Basic Processes | Advanced Processes | Basic Screens | Advanced Screens | Basic Workflows | Advanced Workflows | Access Rights Groups | Objects | Calculated Fields | Basic Wizards | Advanced Wizards | Effort | # days if Effort=4

## Results
Gap Frequency Grid
Critical Level | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | [8 empty] | Cost per complexity
Implementation effort | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | N/A | Total | Control | 1 | 2 | 3 | 4 | 5 | N/A
Sales | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 4 | All Kept | 0 | 0 | 0 | 32000 | TBD
Integration | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 3 | All Kept | 0 | 0 | 0 | 94000 | TBD
Products and Materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 Dropped | 0 | 0 | 0 | 0 | TBD
Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | All Kept | 0 | 0 | 0 | 0 | TBD
Manufacturing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 Dropped | 0 | 0 | 0 | 20000 | TBD
Warehousing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | All Kept | 0 | 0 | 0 | 0 | TBD
Purchasing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 3 | 4 Dropped | 0 | 0 | 0 | 40000 | TBD
Shipping | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 4 Dropped | 0 | 0 | 3000 | 14000 | TBD
Warranty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | All Kept | 0 | 0 | 0 | 0 | TBD
AR-AP | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 2 Dropped | 0 | 0 | 0 | 10000 | TBD
Payroll and HR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | All Kept | 0 | 0 | 0 | 0 | TBD
Accounts Payable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | All Kept | 0 | 0 | 0 | 0 | TBD
Cost Accounting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | All Kept | 0 | 0 | 0 | 0 | TBD
GL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | All Kept | 0 | 0 | 0 | 0 | TBD
Security | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | All Kept | 0 | 0 | 0 | 0 | TBD
Repricing Service Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | All Kept | 0 | 0 | 0 | 0 | TBD
Quality - In-house | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 2 Dropped | 0 | 0 | 3000 | 8000 | TBD
Quality - After Sale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | All Kept | 0 | 0 | 0 | 0 | TBD
Marketing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | All Kept | 0 | 0 | 0 | 0 | TBD
Total Frequency | 0 | 0 | 2 | 11 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 14 | 0 |  | 16
Total Cost | [28 empty] | 0 | 0 | 6000 | 218000
Development efforts per category
Gap Chart
Time and Cost Estimation
Functional Analysis | # | d | =
Design of Basic Reports | 2 | 0.5 | 1
Design of Advanced Reports | 1 | 1 | 1
Design of Basic Processes | 3 | 0.5 | 1.5
Design of Advanced Processes | 4 | 1.5 | 6
Design of Basic Screens | 11 | 0.5 | 5.5
Design of Advanced Screens | 0 | 1.5 | 0
|  |  | 15 | mandays |  |  | at | 4000 |  | /day |  | = | 60000
Technical Analysis | # | d | =
Definition of Basic Workflows | 0 | 1.5 | 0
Definition of Advanced Workflows | 3 | 2.5 | 7.5
Definition of Access Rights Groups | 0 | 0.5 | 0
Definition of Objects | 8 | 0.5 | 4
Definition of Calculated Fields | 0 | 0.125 | 0
Definition of Basic Wizards | 1 | 1 | 1
Definition of Advanced Wizards | 1 | 2 | 2
|  |  | 14.5 | mandays |  |  | at | 4000 |  | /day |  | = | 58000
Development | # | d | =
Implementation Effort Score 1 | 0 | 0.125 | 0
Implementation Effort Score 2 | 0 | 0.25 | 0
Implementation Effort Score 3 | 2 | 0.5 | 1
Implementation Effort Score 4 | 14 | N/A | 52
|  |  | 53 | mandays |  |  | at | 2000 |  | /day |  | = | 106000
Deployment
|  |  | 10 | mandays |  |  | at | 4000 |  | /day |  | = | 40000
Training/Support/Maintenance
Functional training (days) |  |  | 10 |  |  |  |  | 4000 |  |  |  |  | 40000
Odoo Enterprise Contract (per year) |  |  | 60 |  |  |  |  | 1029.12 |  |  |  |  | 61747.2
Total |  |  | 92.5 | mandays | [7 empty] | for | 365747.2